## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Admin | Make Registration Page | I Can Access Test | 1
| SB1/US2 | Student | Register Myself Using Email Id | I Can Receive A Confirmation/Verification Mail | 1
| SB1/US3 | Student | Using User Id | Login By User Name | 2
| SB1/US4 | Student | Using Password | Secured By Password | 1
| SB1/US5 | Student | Login Into The System User Id And Password | I Can View/Edit My Profile | 1
| SB1/US6 | Admin | Authorised User Login | Only Take Tast Authorised User | 1
| SB1/US7 | Student | Modify The Account Password | I Can Keep My Account Secure | 3
| SB1/US8 | Admin | Write Registration Data to the Database | I Can Allow Take Test | 2
2 | SB2/US1 | Admin | Make Exam Pattern Page | I Can Give Test | 1
| SB2/US2 | Admin | Upload Question Type Paper | Show Question Paper Screen | 2
| SB2/US3 | Student | Exam Time Duration | I Can Take Test According To Time Period | 3
| SB2/US4 | Student | Seen Current Question On Screen | I Can Show Only One Question On Screen | 2
| SB2/US5 | Admin | Four Option Per Question | I Can Select Right Question | 1
| SB2/US6 | Admin | Answer Checking System Should Be Available | I Can Checking Answer Right Or Wrong | 1
| SB2/US7 | Admin | Save And Next Question Option | I Can Reach Next Or Previous Question | 2
| SB2/US8 | Student | Remark Option On Perticuler Question | I Can Remark On Perticuler Question | 3
| SB2/US9 | Student | Submit Test After Time Duration | Submit Test After Complete | 1
3 | SB3/US1 | Admin | Result Upload | Indivisual Performance Checking | 1
| SB3/US2 | Admin | Performance Analysis | Monthly/Weekly Report | 2
| SB3/US3 | Student | Seen Previous Result | I Can Show My Previous Performance | 2
| SB3/US4 | Student | Practice Session | I Can practice Check Performance | 3
| SB3/US5 | Student | Log Out After The Over | I Can Log Out After Complete Test | 1
| SB3/US6 | Student | Give Feedback/Suggestion | The Way Of Work Are Improvement | 2
4 | SB4/US1 | Student | Edits MY Profile Details | Any Changes
| SB4/US2 | Admin | Admin Panel | Admin User Can Manage Every Task
| SB4/US3 | Admin | Uploaded New Question Paper | Changes Test Question
| SB4/US4 | Admin | Changes Project Update | I Can Changes New Updates In Project

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID |  | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 | Create A Home Page | SB1/D1/T1 | Authorised User Login
|  | SB1/D1/T2 | Login By User Name
|  | SB1/D1/T3 | Login By Password
|  | SB1/D1/T4 | Forget Password Option
|  | SB1/D1/T5 | New User Registration
|  | SB1/D1/T6 | Login Data From Database
SB1/US2 | Create a Registration Page | SB1/D2/T1 | Registration Using First Name
|  | SB1/D2/T2 | Registration Using Username
|  | SB1/D2/T3 | Registration Using Secure Password
|  | SB1/D2/T4 | Registration Using Email Id
|  | SB1/D2/T5 | Registration Contact Number
SB1/US3 | Create A Registration Page | SB1/D3/T1 | Registration Using Date Of Birth
|  | SB1/D3/T2 | Registration Using City Address
|  | SB1/D3/T3 | Registration Using Area Code
|  | SB1/D3/T4 | Registration Using Sequerity Question Option
SB1/US4 | Create A Student Page | SB1/D4/T1 | Previous Saved Test Result
|  | SB1/D4/T2 | Edits Profile Picture
|  | SB1/D4/T3 | LogOut Option
|  | SB1/D4/T4 | Change Password Option
|  | SB1/D4/T5 | Changes Profile Details

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 180 | Tasks
2018-09-12 | 120 | 180
2018-09-11 | 80 | 180
2018-09-14 | 56 | 180
2018-09-16 | 15 | 180
2018-09-18 | 5 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
SB2/US1 | Create A Question Screen Page | SB2/D1/T1 | Categories Type Exam
|  | SB2/D1/T2 | Make Exam Pattern Page
|  | SB2/D1/T3 | Upload Question Type Paper
SB2/US2 | Create Home Page Exam Test | SB2/D2/T1 | Exam Time Duration
|  | SB2/D2/T2 | Seen Current Question On Screen
|  | SB2/D2/T3 | Four Option Per Question
|  | SB2/D2/T4 | Answer Checking System Should Be Available
|  | SB2/D2/T5 | Save And Next Question Option
SB3/US3 | Create Test Screen Online Exam | SB2/D3/T1 | Remark Option On Perticuler Question
|  | SB2/D3/T2 | Submit Test After Time Duration
|  | SB2/D3/T3 | Show Test Result After Over Exam
|  | SB2/D3/T4 | Exit Test Screen

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>
SB3/US1 | Create Test Result Performance Page | SB3/D1/T1 | Check Current Test Result
|  | SB3/D1/T2 | Result Upload
|  | SB3/D1/T3 | Performance Analysis
SB3/US2 | Create Test Screen Practice Session Page | SB3/D2/T1 | Seen Previous Result
|  | SB3/D2/T2 | Practice Session
|  | SB3/D2/T3 | Log Out Profile After Complete Test
|  | SB3/D2/T4 | Give Feedback/Suggestion

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>
SB4/US1 | Create Admin Panel Page | SB4/D1/T1 | Edits MY Profile Details
|  | SB4/D2/T2 | Admin Panel
|  | SB4/D3/T3 | Uploaded New Question Paper
SB4/US2 | Admin Updates | SB4/D4/T4 | Changes New Updates
SB4/D5/T5

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days