## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Admin | Make Registration Page | I Can Access Test | 1
| SB1/US2 | Student | Register Myself Using Email Id | I Can Receive A Confirmation/Verification Mail | 1
| SB1/US3 | Student | Using User Id | Login By User Name | 2
| SB1/US4 | Student | Using Password | Secured By Password | 1
| SB1/US5 | Student | Login Into The System User Id And Password | I Can View/Edit My Profile | 1
| SB1/US6 | Admin | Authorised User Login | Only Take Tast Authorised User | 1
| SB1/US7 | Student | Modify The Account Password | I Can Keep My Account Secure | 3
| SB1/US8 | Admin | Write Registration Data to the Database | I Can Allow Take Test | 2
2 | SB2/US1 | student | Make Exam Pattern Page | I Can Give Test | 1
| SB2/US2 | student | Upload Question Type Paper | Show Question Paper Screen | 2
| SB2/US3 | Student | Exam Time Duration | I Can Take Test According To Time Period | 3
| SB2/US4 | Student | Seen Current Question On Screen | I Can Show Only One Question On Screen | 2
| SB2/US5 | student | Four Option Per Question | I Can Select Right Question | 1
| SB2/US6 | student | Answer Checking System Should Be Available | I Can Checking Answer Right Or Wrong | 1
| SB2/US7 | student | Save And Next Question Option | I Can Reach Next Or Previous Question | 2
| SB2/US8 | Student | Remark Option On Perticuler Question | I Can Remark On Perticuler Question | 3
| SB2/US9 | Student | Submit Test After Time Duration | Submit Test After Complete | 1
3 | SB3/US1 | Admin | Manage Result | Indivisual Performance Checking | 1
| SB3/US2 | Admin | Manage Users | Monthly/Weekly Report | 2
| SB3/US3 | admin | Praepare Question | I Can update new question | 2
| SB3/US4 | admin | Manage test | I Can manage all cetegeries test | 3
| SB3/US5 | admin | Log Out After Over | I Can Log Out After Complete Test | 1
| SB3/US6 | admin | Manage Test Subject | Indivisual Test are Coducted | 2
4 | SB4/US1 | admin | Edits MY Profile Details | Any Changes
| SB4/US2 | Admin | Admin Panel | Admin User Can Manage Every Task
| SB4/US3 | Admin | Uploaded New Question Paper | Changes Test Question
| SB4/US4 | Admin | Manage Question | I Can Changes New Updates In Project
| SB4/US5 | admin | Manage Result | Access all users Result
| SB5/US6 | Admin | Create Database | filled data inforamtion tables

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID |  | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 | Create A Home Page | SB1/D1/T1 | Authorised User Login | IK | Completed
|  | SB1/D1/T2 | Login By Roll No | SG | Completed
|  | SB1/D1/T3 | Login By Password | SG | Completed
|  | SB1/D1/T4 | Forget Password Option | SG | Completed
|  | SB1/D1/T5 | New User Registration | IK | Completed
|  | SB1/D1/T6 | Login Data From Database | IK | Completed
SB1/US2 | Create a Registration Page | SB1/D2/T1 | Registration Using First Name | IK | Completed
|  | SB1/D2/T2 | Registration Using Username | IK | Completed
|  | SB1/D2/T3 | Registration Using Secure Password | SG | Completed
|  | SB1/D2/T4 | Registration Using Email Id | IK | Completed
|  | SB1/D2/T5 | Registration Contact Number | IK | Completed
SB1/US3 | Create A Registration Page | SB1/D3/T1 | Registration Using Date Of Birth | IK | Completed
|  | SB1/D3/T2 | Registration Using City Address | SG | Completed
|  | SB1/D3/T3 | Registration Using Area Code | SG | Completed
|  | SB1/D3/T4 | Registration Using Sequerity Question Option | IK | Completed

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1
2
3
4
0
0
5 | [5 empty] | 0
0
6
7
8
9
10
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 180 | Tasks
2018-09-12 | 120 | 180
2018-09-11 | 80 | 180
2018-09-14 | 56 | 180
2018-09-16 | 15 | 180
2018-09-18 | 5 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
SB2/US1 | Create A Question Screen Page | SB2/D1/T1 | Categories Type Exam | IK | Completed
|  | SB2/D1/T2 | Make Exam Pattern Page | SG | Completed
|  | SB2/D1/T3 | Upload Question Type Paper | SG | Completed
SB2/US2 | Create Home Page Exam Test | SB2/D2/T1 | Exam Time Duration | SG | Completed
|  | SB2/D2/T2 | Seen Current Question On Screen | IK | Completed
|  | SB2/D2/T3 | Four Option Per Question | IK | Completed
|  | SB2/D2/T4 | Answer Checking System Should Be Available | IK | Completed
|  | SB2/D2/T5 | Save And Next Question Option | IK | Completed
SB3/US3 | Create Test Screen Online Exam | SB2/D3/T1 | Remark Option On Perticuler Question | SG | Completed
|  | SB2/D3/T2 | Submit Test After Time Duration | IK | Completed
|  | SB2/D3/T3 | Show Test Result After Over Exam | IK | Completed
|  | SB2/D3/T4 | Exit Test Screen | IK | Completed

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>
SB3/US1 | Create Test Result Performance Page | SB3/D1/T1 |  | IK | Completed
|  | SB3/D1/T2 | Marksheet Result | IK | Completed
|  | SB3/D1/T3 | check Users performance | SG | Completed
SB3/US2 | Create Test Screen Practice Session Page | SB3/D2/T1 | Praepare Question | SG | Completed
|  | SB3/D2/T2 | Manage test | IK | Completed
|  | SB3/D2/T3 | Log Out After Over | SG | Completed
|  | SB3/D2/T4 | Manage Test Subject | IK | Completed
SB3/US3 | Create A Student Page | SB3/D3/T1 | Previous Saved Test Result | IK | Completed
|  | SB3/D3/T2 | Edits Profile Picture | SG | Completed
|  | SB3/D3/T3 | LogOut Option | SG | Completed
|  | SB3/D3/T4 | Change Password Option | IK | Completed
|  | SB3/D3/T5 | Changes Profile Details | IK | Completed

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>
SB4/US1 | Create Admin Panel Page | SB4/D1/T1 | Edits MY Profile Details | IK | Completed
|  | SB4/D2/T2 | Admin Panel | IK | Completed
|  | SB4/D3/T3 | Uploaded New Question Paper | IK | Completed
SB4/US2 | Admin Updates | SB4/D4/T4 | Manage Question | IK | Completed
|  | SB4/D5/T5 | Manage Result | IK | Completed
|  | SB5/D5/T6 | Create Database | IK | Completed

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days